## Project_Details
a | b
Project ID | 9
Name | Around the World in Eighty Days
Project Manager | Honorine
Project Lead | Jules
Scope | Circumnavigate the world in 80 days, to win the 20,000 GBP wager at the Reform Club
Objectives | Win the bet

## Plan
No | Phase | Task | Responsible | Status | Start | End | Duration (days)
1.1 | Preparations | Agree on wager | Phileas | Complete | 2020-03-15 | 2020-03-15
1.2 | Preparations | Prepare Trip | Valet | Complete | 2020-03-15 | 2020-03-20
2.1 | Trip | London to Suez, Egypt | Phileas | Complete | 2020-03-20 | 2020-03-27 | 7
2.2 | Trip | Suez to Mumbia, India | Phileas | Complete | 2020-03-27 | 2020-04-09 | 13
2.3 | Trip | Mumbai to Kolkata, India | Phileas | Complete | 2020-04-09 | 2020-04-12 | 3
2.4 | Trip | Kolkata to Hong Kong with a stopover in Singapore | Phileas | Complete | 2020-04-12 | 2020-04-25 | 13
2.5 | Trip | Hong Kong to Yokohama, Japan | Phileas | Complete | 2020-04-25 | 2020-05-01 | 6
2.6 | Trip | Yokohama to San Francisco, United States | Phileas | In Progress | 2020-05-01 | 2020-05-23 | 22
2.7 | Trip | San Francisco to New York City, United States | Phileas | To Do | 2020-05-23 | 2020-05-30 | 7
2.8 | Trip | New York to London | Phileas | To Do | 2020-05-30 | 2020-06-08 | 9
2.8 | Trip | Finish Trip at Reform Club | Phileas | To Do | 2020-06-08 | 2020-06-08
3.1 | Wrap-up | Collect Prize | Phileas | To Do | 2020-07-15 | 2020-07-15
Formulas:
Start = [End, row above]
End = [Start]+[Duration (days)]
End = [Duration (days)]+[Start]

## Updates
Date | Done | To Do
2020-03-15 | Challenge accepted | Prepare logistics
2020-03-20 | Tickets bought. Hired new valet, Passepartout | Start trip
2020-03-31 | Completed trip to Suez, and embarked to Mumbai on the Mongolia | Arrive to Mumbai, go to Kolkata and seek passage to Hong Kong
2020-04-15 | Crossed through India, faced issues on the leg between "Kholby to Prayagraj". Boarded the Rangoon towards Hong Kong. Rescued Auoda. | Continue trip to from Hong Kong to Yokohama, Japan.
2020-04-30 | Sought passage Hong Kong-Yokohama on the Carnatic (after minor delays). | Arrive to Yokohama and seek passage to San Francisco
2020-05-15 | Pacific crossing in progress. | Arrive to San Francisco.

## Issues
Severity | State | Issue | Impact | Action | Due | Assignee
G | Closed | Forster brought shaving water at the wrong temperature | Fired Forster, without a reference. | Hired new valet. | 2020-03-20 | Phileas
A | Closed | Being informed there was no road between "Kholby " and "Allahabad", Phileas bought an elephant. Kholby does not exist and there is a direct train between Mumbai and Kolkata. | Need to find a new home for the elephant | Find an elephant sanctuary and get the elephant there. | 2020-04-12 | Passepartout